## Test Plan
Please click here to display in PDF format.

## Mind Maps
Mind Map of Truck Lagbe Website

## Test Scenarios
Project Name | Bug Lagbe | Reference Document | FRS
Written by | Samira Siddiqua | Creation Date | 2025-03-05
Test Scenario ID | Module | Test Scenario | No. of Test Cases | Priority
TS-01 | User Management | Validate successful user registration. | 4 | High (P1)
TS-02 |  | Validate login with valid and invalid credentials. | 4 | High (P1)
TS-03 |  | Validate a user can log out successfully. | 6 | High (P1)
TS-04 |  | Validate OTP functionality. | 2 | High (P1)
TS-05 |  | Validate users can update personal details (name, email, etc.). | 5 | Medium (P2) to High (P1)
TS-06 | Truck Booking Panel | Validate user can create a new trip with valid inputs. | 6 | High (P1)
TS-07 |  | Validate truck selection and display of truck details. | 4 | High (P1)
TS-08 |  | Validate bidding, bid updates, booking and trip details. | 7 | High (P1)
TS-09 |  | Validate trip cancellation and history. | 2 | Medium (P2) to High (P1)
TS-10 | Customer Support | Validate live chat functionality. | 9 | High (P1)
TS-11 |  | Validate FAQ accessibility and functionality. | 6 | Medium (P2)
TS-12 |  | Validate support ticket submission and tracking. | 5 | Medium (P2) to High (P1)
TS-14 | Global Components | Validate header functionality. | 7 | High (P1)
TS-15 |  | Validate footer functionality. | 5 | Medium (P2)
TS-17 |  | Validate UI/UX Elements (CTA Buttons). | 4 | Medium (P2)
TS-18 | Blog | Validate blog content organization. | 4 | High (P1)
TS-20 |  | Validate blog search functionality and user engagement. | 6 | Medium (P2)
TS-23 | Security | Validate XSS (Cross-Site Scripting) protection on user inputs. | 3 | High (P1)
TS-24 |  | Validate SQL Injection Protection on search and booking forms. | 3 | High (P1)
TS-25 |  | Validate Multi-Factor Authentication (MFA) for user login. | 3 | High (P1)
TS-27 |  | Validate data backup and recovery mechanism for booking data. | 2 | Medium (P2)
TS-28 | Accessibilty | Validate keyboard navigation functionality. | 3 | High (P1)
TS-29 |  | Validate screen reader support. | 2 | High (P1)
TS-30 |  | Validate high contrast mode. | 2 | Medium (P2)
TS-31 |  | Validate multi-language support. | 2 | Medium (P2)

## Test Cases
Project Name | Bug Lagbe | Test Case Start Date | 2025-03-05 | Test Case Author | Samira Siddiqua | [5 empty] | Status | Test Cases
Description | A manual testing project ensuring a smooth, bug-free ride for Truck Lagbe website users. | Test Case End Date | Ongoing | Test Case Reviewer | Ehsanul Alam Sabbir | [5 empty] | Passed | 76
Website under testing | https://trucklagbe.com/ | [9 empty] | Failed | 19
[11 empty] | Not executed | 11
[11 empty] | Blocked | 0
[11 empty] | Total | 106
#SL | Module | Type of Testing | Features | Test Cases | Expected Results | Actual Results | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status | Remarks
1 | User Management |  | Registration | Verify a new user can register successfully with valid details. | Registration is successful. The system redirects the user to the dashboard or login page. A "Welcome" notification is received on the dashboard. | ✅ Registration completed successfully. ✅ The user was redirected to the dashboard. |  | 1. Open the Truck Lagbe website. 2. Navigate to the Registration page. 3. Enter valid details: Phone Number (unique) 4. Click "Continue". 5. Enter OTP received via SMS. 6. Click "Submit". |  |  | PASSED
2 |  |  |  | Verify that adding/updating an email in the user profile triggers a correctly formatted confirmation email with a working verification link. | A confirmation email with correct formatting and a working verification link is sent to the updated email, and clicking the link successfully verifies the email on the Truck Lagbe website. | ❌ Verification link leads to: Cannot GET /appApi/117/confirm/userEmailVerification. |  | 1. Click "Add/Update Email" and save a new email. 2. Open the confirmation email and click the verification link. 3. Check the profile. |  |  | FAILED
3 |  |  |  | Confirm that clicking the "Resend Verification Email" button successfully delivers a new, functional link if the initial one fails. | 1. System sends a new email within 1-2 minutes. 2. Link works; email is verified successfully. 3. Email status updates to "Verified". | ❌ No email received after clicking "Resend". |  | 1. Click "Resend Verification Email".​ 2. Open the new email and click the link. 3. Check the profile. |  |  | PASSED
4 |  |  |  | Verify that new users must verify their account using OTP. | OTP verification is successful. The user is redirected to the dashboard or login page. | ✅ The OTP was received via SMS. ✅ After entering the correct OTP, registration was completed. ✅ The user was redirected to the dashboard. |  | 1. Enter valid registration details and click Register. 2. Receive OTP via SMS/email. 3. Enter the correct OTP. 4. Click Verify & Complete Registration. |  |  | PASSED
5 |  |  | Login | Verify that the user can log in with valid credentials. | The user should be successfully logged in. The user should be redirected to their dashboard or the homepage. A welcome message should appear, confirming the login. | ✅ User successfully logged in and redirected to the dashboard. ✅ Welcome message displayed. |  | 1. Open the Truck Lagbe website. 2. Click on the Login button. 3. Enter the valid phone number. 5. Click the Login button. |  |  | PASSED
6 |  |  |  | Verify Session Expiry Warning and Timeout Behavior | Warning appears after expected idle time. "Continue Working" keeps the session alive. "Logout" or timeout forces logout correctly. | ✅ Warning appears as expected. |  | 1. Log in to the application. 2. Do not perform any actions (stay idle). 3. Observe if the warning message appears after a set time (e.g., 15-30 minutes). 4. Expected: A modal appears with: Message: "Still with us? You've been away for a while..." Buttons: "Continue Working" and "Logout" |  |  | PASSED
7 |  |  |  | Absence of "Remember Me" Functionality | No "Remember Me" checkbox visible. Session expires; requires new OTP on revisit. | ✅ Absent |  | 1. Open Truck Lagbe login page. 2. Log in with OTP → Close browser. 3. Check browser cookies/local storage. |  |  | PASSED
8 |  |  |  | Inability to Deactivate/Suspend User Account | User should see a "deactivate button" and receive a confimation message after clicking it. The account should be marked as deactivated and inaccessible without reactivation. | ❌ No option to deactivate the account is available in the user interface. User is unable to proceed with deactivation. |  | 1. Navigate to https://www.trucklagbe.com 2. Log in using valid credentials 3. Go to the Account Settings or Profile section 4. Look for an option labeled "Deactivate Account", "Close Account", or similar 5. Click on the Deactivate Account button (if available) |  |  | FAILED
9 |  |  | Logout | Verify that a user can log out successfully from the website. | The user should be logged out successfully. The system should redirect the user to the login page or display the home page with no user session active. The user’s session should be terminated, and the login button should be visible instead of the user profile. | ✅ The user was logged out successfully. ✅ The user was redirected to the login page. ✅ The login button was visible, and the user profile was no longer visible. |  | 1. Open the Truck Lagbe website. 2. Log in with valid credentials. 3. Once logged in, click on the profile icon or logout button (usually located in the header or user profile section). 4. Click on the Logout option. |  |  | PASSED
10 |  |  |  | Verify that after logging out, pressing the browser’s back button does not retain cached authenticated content and instead enforces immediate session termination. | The user should not be able to access any of the previous pages that require an active session. The website should redirect the user back to the login page if they try to access any secure page using the back button. | ❌ After pressing the back button: The dashboard page loads for several minutes (extended delay). Eventually, it confirms the logged-out state. Reproducible in both Chrome and Edge. |  | 1. Log in to the Truck Lagbe website. 2. Log out from the website using the Logout button. 3. After being redirected to the login page, click on the browser back button. |  |  | FAILED
11 |  |  |  | Verify that the session expires after logging out and cannot be restored. | The user should be logged out, and no session should be active. The user should be directed to the login page upon visiting the website again. | ✅ The user was redirected to the login page after reopening the browser. ✅ The session was not restored, and the user had to log in again. |  | 1. Log in to the Truck Lagbe website. 2. Log out from the website using the Logout button. 3. After logging out, close the browser. 4. Reopen the browser and try to access the Truck Lagbe website. |  |  | PASSED
12 |  |  |  | Verify that the Logout button is visible only after the user has logged in. | The Logout button should be invisible before login. The Logout button should become visible only after the user logs in. | ✅ The Logout button was not visible before logging in. ✅ The Logout button became visible after logging in successfully. |  | 1. Open the Truck Lagbe website. 2. Ensure that the Logout button is not visible before logging in. 3. Log in using valid credentials. 4. After successful login, check if the Logout button becomes visible. |  |  | PASSED
13 |  |  |  | Verify that logging out doesn't result in any unexpected errors or broken functionality. | The system should not throw any errors like "500 Internal Server Error" or other unexpected issues after logout. The system should behave normally after logout, with no broken functionality. | ✅ No errors were encountered after logging out. ✅ The website operated normally after logout, and there were no system failures or issues. |  | 1. Log in to the Truck Lagbe website. 2. Log out from the website using the Logout button. 3. After logging out, perform actions like refreshing the page, navigating back to the homepage, or visiting other non-logged-in pages. |  |  | PASSED
14 |  |  |  | Verify that logging out from one tab logs out the user in all other open tabs. | The user should be logged out from all open tabs after logging out from one tab. The system should prompt the user to log in again if they try to access a restricted page on any other tab. | ✅ The user was logged out from both tab 1 and tab 2 after logging out from tab 1. ✅ Access was blocked on tab 2, and the login page appeared. |  | 1. Log in to the Truck Lagbe website in multiple tabs (e.g., tab 1 and tab 2). 2. Log out from tab 1. 3. Switch to tab 2 and try to access the user's account or restricted page. |  |  | PASSED
15 |  |  | OTP | Verify OTP Validation Error Messaging | 1. Error: "Wrong OTP entered. Try again." 2. Error: "Wrong OTP entered. 1 attempt left." 3. Error: "Too many attempts. Wait 1 hour or call helpline." 4. Error: "Wait 1 hour before retrying." | ✅ 1. Error: "The code you have entered is incorrect." 2. Error: "The code you have entered is incorrect." 3. Message: "Not Getting Verification Code? [Helpline]. Wait 1 hour before retrying." |  | 1. Submit 1st wrong OTP (e.g., "123456"). 2. Submit 2nd wrong OTP. 3. Submit 3rd wrong OTP. 4. Attempt OTP resend during cooldown. |  |  | PASSED
16 |  |  |  | Verify OTP resend functionality and anti-spam measures. | "Resend Code" option appears after 30–60 seconds. After 3–5 attempts, system enforces rate-limiting (e.g., "Try again in 15 minutes"). No OTP sent during cooldown. | ✅"Resend Code" button appeared after 30 seconds (as expected). On the 3rd attempt, system displayed: "If your number is correct, try again after 1 hour or call helpline." |  | 1. Navigate to the Truck Lagbe login page. 2. Enter a registered mobile number in the Mobile No. field. 3. Click Continue to request an OTP. 4. Do not enter OTP; click Resend OTP (if available). 5. Repeat OTP request 5 times consecutively. 6. Check if the system blocks further requests. |  |  | PASSED
17 |  |  | Profile Configuration | Verify that a user can successfully update their name with valid input. | The name should be updated successfully and displayed correctly on the profile page. | ✅ The name was updated successfully and displayed correctly. |  | 1. Navigate to the Profile Settings page. 2. Locate the Name field and enter a new valid name (e.g., "John Doe"). 3. Click on the Save/Update button. 4. Refresh the page and check if the updated name is displayed. |  |  | PASSED
18 |  |  |  | Verify that the system prevents updating the name with invalid input. | The system should display an error message indicating invalid input. The name should not be updated. | ❌ System accepts all invalid names (numbers, special characters, single letters) without validation or error messages. |  | 1. Navigate to the Profile Settings page. 2. Enter an invalid name containing special characters or numbers (e.g., "J0hn D0e!@#"). 3. Click on the Save/Update button. |  |  | FAILED
19 |  |  |  | Verify that a user can successfully update personal details when the internet connection is slow or unstable. | The system should handle slow internet gracefully. If the request fails, the user should receive a clear error message or an auto-retry option. No partial updates or data loss should occur. | ✅ The system showed a loading indicator and successfully saved the data when the connection was restored. ✅ No data corruption occurred. |  | 1. Navigate to the Profile Settings page. 2. Enter a new name, phone number, and address. 3. Reduce internet speed (e.g., disconnect and reconnect Wi-Fi or enable "Slow 3G" in browser dev tools). 4. Click the Save/Update button. 5. Observe system behavior (e.g., loading time, error messages, retry mechanisms). 6. Refresh the page to check if the changes were saved. |  |  | PASSED
20 |  |  |  | Verify that profile updates from multiple devices or browser sessions do not cause data inconsistency. | The system should handle concurrent updates properly. Either the latest update should overwrite the previous one, or the system should prompt the user about conflicting changes. No data corruption or inconsistency should occur. | ✅ The system saved the last update correctly without inconsistencies. ✅ No data corruption occurred. |  | 1. Device 1: Open the Profile Settings page and enter a new name (e.g., "John Doe Updated"). 2. Device 2: Open the Profile Settings page and enter a different name (e.g., "John D."). 3. Device 1: Click the Save/Update button first. 4. Device 2: Click the Save/Update button after Device 1 has already saved changes. 5. Refresh both devices and check which data is retained. |  |  | PASSED
21 |  |  |  | Verify that a user can successfully upload and update their profile photo. | The profile photo should be successfully updated and displayed on the user's profile. | ❌ Failure Observed: Thumbnail preview works, but clicking Update does nothing (no API call, no error). After refresh, the old/default image remains (upload failed silently). |  | 1. Navigate to the Profile Settings page. 2. Click on the profile picture section to upload a new photo. 3. Select a valid image file (e.g., JPG, PNG, or JPEG within the allowed size limit). 4. Click the Upload/Save button. 5. Refresh the page to check if the updated profile picture is displayed correctly. |  |  | FAILED
22 | Truck Booking Panel |  | Trip Creation Process | Verify that the user can successfully create a new trip with all valid details (pickup, drop-off, date, truck type, etc.). | The system should successfully create the trip and display a confirmation message with correct trip details (pickup, drop-off, truck type, date). The trip should be added to the user's upcoming trip list. | ✅ The system successfully created the trip and displayed the correct trip details. The trip was added to the user's upcoming trip list. |  | 1. Log in to the website as a registered user. 2. Navigate to the "Create Trip" section. 3. Fill in valid details for all required fields (pickup location, drop-off location, trip date, truck type). 4. Click the "Create Trip" button. |  |  | PASSED
23 |  |  |  | Verify that the system displays an error message when the pickup location is missing during trip creation. | The system should display an error message: "Pickup location is required." The trip should not be created. | ✅ The system displayed the message "Please select a valid address" and prevented the trip from being created. |  | 1. Log in to the website as a registered user. 2. Navigate to the "Create Trip" section. Leave the pickup location field blank and enter the remaining details (drop-off location, date, truck type). 3. Click the "Create Trip" button. |  |  | PASSED
24 |  |  |  | Verify that the user can successfully create a trip when all required fields are filled, and the input data is valid. | The system should create the trip successfully, show a confirmation message with the trip details, and add the trip to the user's upcoming trip list. | ✅ The system successfully created the trip, displayed the correct details, and added the trip to the user's upcoming trip list. |  | 1. Log in to the website as a registered user. 2. Navigate to the "Create a New Trip" section. 3. Fill in all the required details (pickup location, drop-off location, date, truck type). 4. Click the "Create Trip" button. |  |  | PASSED
25 |  |  |  | Verify that the system prevents the user from creating a trip if an invalid truck type is selected. | The system should display an error message: "Please select a valid truck type." The trip should not be created. | ✅ The system did not display an error message but prevented the trip from being created. |  | 1. Log in to the website as a registered user. 2. Navigate to the "Create a New Trip" section. 3. Fill in valid details for pickup location, drop-off location, and date. 4. Select an invalid truck type (e.g., a type not available in the system). 5. Click the "Create Trip" button. |  |  | PASSED
26 |  |  |  | Verify that the system allows users to create a trip with today's date as the trip date. | The system should successfully create the trip and display a confirmation message with the correct trip details (pickup, drop-off, truck type, date). The trip should be added to the user's upcoming trip list. | ✅ The system successfully created the trip, displayed the correct details, and added the trip to the user's upcoming trip list. |  | 1. Log in to the website as a registered user. 2. Navigate to the "Create a New Trip" section. 3. Enter valid details for pickup location, drop-off location, and truck type. 4. Select today's date in the trip date field. 5. Click the "Create Trip" button. |  |  | PASSED
27 |  |  |  | Verify that the system allows trip creation for any future time (24/7 operation) and does not enforce same-day cutoffs, as per business requirements. | System accepts only future dates/times (including same-day future times) and rejects past times. | ✅ System accepts all future times (24/7 operation). |  | 1. Navigate to Create New Trip page. 2. Open the date/time picker for the trip start field. 3. Attempt to select: Current date + future time (e.g., today at 3 AM if current time is 2 AM) |  |  | PASSED
28 |  |  | Truck Selection | Verify that the system filters trucks based on the selected size preference. | The system displays only trucks that match the selected size filter. | ✅ The system displayed trucks that matched the selected size (Small, Medium, Large). |  | 1. Log in to the website as a registered user. 2. Navigate to the "Select a Truck" section. 3. Select "Truck Size" as the filter preference (e.g., Small, Medium, Large). 4. Apply the filter. 5. Verify if the system displays trucks that match the selected size. |  |  | PASSED
29 |  |  |  | Verify that the truck's capacity is displayed correctly. | The truck's capacity is displayed correctly on the truck details page. | ✅ The truck's capacity (e.g., 10 tons) was displayed correctly. |  | 1. Log in to the website as a registered user. 2. Navigate to the "Select a Truck" section. 3. Select a truck from the available list. 4. Verify if the truck's capacity is displayed accurately (e.g., 10 tons, 500 kg). |  |  | PASSED
30 |  |  |  | Verify Truck Model Number Display Validation | All trucks display accurate, complete model identification. | ✅ The model numbers are displayed correctly. |  | 1. Open any truck listing from search results 2. Navigate to "Truck Specifications" section 3. Verify presence of: Manufacturer name (e.g., "Ashok Leyland") Complete model number (e.g., "AL 3525 6x4") |  |  | PASSED
31 |  |  |  | Verify Cargo Compatibility Information | Each truck shows minimum 1 valid cargo type. | ✅ All trucks listed accurate cargo types. |  | 1. Select 3 random trucks from listings. 2. Check each "Cargo Specifications" section for: Listed cargo types (e.g., "Dry Goods, Electronics"). |  |  | PASSED
32 |  |  | Bidding and booking | Verify that truck owners can place bids for a user’s trip request. | The system should allow the truck owner to place a valid bid for the user's trip. | ✅ The truck owner successfully placed a bid for the trip, and it was displayed in the bidding section. |  | 1. A user posts a trip request. 2. A truck owner places a bid for the trip. |  |  | PASSED
33 |  |  |  | Verify that users receive real-time bid updates from truck owners. | The user should receive real-time notifications of new bids placed by truck owners. | ✅ The user received real-time notifications for each new bid placed. |  | 1. A user posts a trip request. 2. Truck owners place bids. 3. Monitor the user's account for real-time bid updates. |  |  | PASSED
34 |  |  |  | Verify that users can view different truck bids placed by truck owners. | The user should be able to view all the truck bids placed for the trip. | ✅ The user was able to view all the placed bids, including truck details and pricing. |  | 1. A user posts a trip request. 2. Truck owners place bids. 3. Verify that the user can view all the bids. |  |  | PASSED
35 |  |  |  | Verify that the system highlights the lowest bid for easy selection by the user. | The system should automatically highlight the lowest bid for easy selection. | ✅ The lowest bid was placed on the top of the list for easy selection. |  | 1. A user posts a trip request. 2. Multiple bids are placed by truck owners. 3. Verify that the lowest bid is visually highlighted on the screen. |  |  | PASSED
36 |  |  |  | Verify that users can accept a bid and receive confirmation of their action. | The system should allow the user to accept a bid and provide a confirmation message. | ✅ The user successfully accepted a bid, and the system displayed a confirmation message. |  | 1. A user posts a trip request. 2. Truck owners place bids. 3. The user accepts or rejects a bid. |  |  | PASSED
37 |  |  |  | Verify that users cannot accept more than one bid for the same trip. | The system should allow the user to accept only one bid for the trip and reject the others. | ✅ The system only allowed the user to accept one bid, and other bids were automatically rejected. |  | 1. A user posts a trip request and receives multiple bids. 2. The user tries to accept more than one bid. |  |  | PASSED
38 |  |  |  | Verify that booking confirmation and trip details are correctly displayed to the user after the booking is completed. | The booking confirmation page should correctly display the following trip details: Pickup location Drop-off location Trip date and time Truck type Total fare | ✅ The booking confirmation page displayed the correct trip details, including all relevant information such as pickup/drop-off location, date, truck type and fare. |  | 1. The user selects a truck and completes the booking process for the trip. 2. After successful payment, the system should display a booking confirmation page. 3. The booking confirmation should include the trip details, such as pickup location, drop-off location, date, truck type, fare, and driver details. |  |  | PASSED
39 |  |  | Trip Cancellation | Verify that users can cancel a booked trip before the scheduled start time. | The system should allow the user to cancel the trip before the start time. | ✅ The trip was successfully canceled using truck lagbe helpline. |  | 1. User logs into the Truck Lagbe website. 2. User navigates to "My Trips" or "Booking History." 3. User selects an upcoming trip. 4. User calls helpline to cancel upcoming trip. |  |  | PASSED
40 |  |  |  | Validate that canceled trips remain in booking history and are marked as "Canceled." | The system should retain canceled trips in history and mark them correctly. | ✅ The canceled trip was correctly displayed in the booking history with a "Canceled" status. |  | 1. User cancels a trip. 2. User navigates to "Booking History." 3. System displays the canceled trip with appropriate status. |  |  | PASSED
41 | Customer Support |  | Live Chat | Verify that the live chat feature is accessible on the Truck Lagbe website. | The live chat icon should be visible on all pages, and users should be able to open the chat window. | ✅ The live chat icon was visible on all pages, and clicking on it opened the chat window successfully. |  | 1. Visit the Truck Lagbe website. 2. Check the visibility of the live chat icon on most pages. 3. Click the chat icon to open the live chat window. |  |  | PASSED
42 |  |  |  | Verify that users can initiate a live chat conversation. | When the user clicks the live chat icon, the system should prompt the user to begin the chat with an agent. | ✅ The chat window prompted the user to select Bengali or English, and the conversation started with an agent. |  | 1. Visit the Truck Lagbe website. 2. Click the live chat icon to open the chat window. 3. Enter the required details. |  |  | PASSED
43 |  |  |  | Verify that users can send and receive messages during a live chat session. | The user should be able to send a message, and the agent should be able to reply in real-time. | ✅ The user sent a message, and the agent responded in real-time. |  | 1. Open the live chat window. 2. Send a message to the agent. 3. Wait for the agent’s reply. |  |  | PASSED
44 |  |  |  | Verify that the chat window displays the entire conversation history during an active session. | All messages sent and received during the chat session should be displayed in the chat window. | ✅ The entire conversation history was visible in the chat window. |  | 1. Open the live chat window. 2. Send multiple messages. 3. Observe if all messages are visible in the conversation history. |  |  | PASSED
45 |  |  |  | Verify that users can exit the chat and the conversation history is saved. | The user should be able to close the chat window, and the chat history should be saved and accessible when reopening the chat. | ✅ The chat window was closed successfully, and upon reopening, the chat history was visible. |  | 1. Open the live chat window. 2. Send a few messages. 3. Close the chat window. 4. Reopen the chat window to check if the history is saved. |  |  | PASSED
46 |  |  |  | Verify that the system supports file attachments during live chat. | The user should be able to attach files (e.g., images or documents) and send them to the agent. | ✅ The user successfully attached and sent a file (image) during the chat. |  | 1. Open the live chat window. 2. Click the Attach File button. 3. Select a file to upload and send it to the agent. |  |  | PASSED
47 |  |  |  | Verify that the live chat window is responsive and works across different screen sizes. | The chat window should adjust its layout appropriately on different screen sizes (e.g., desktop, tablet, mobile). | ❌ Live chat widget cuts off on small screens. |  | Open the Truck Lagbe website on a desktop, tablet, and mobile device. Verify the responsiveness of the chat window. |  |  | FAILED
48 |  |  |  | Verify that a live chat agent responds to user queries within an acceptable time frame (≤ 2 minutes). | Agent responds within ≤ 2 minutes. | ❌ The live chat agent did not respond to the pricing query within the 2-minute timeframe (no response received ultimately). |  | 1. Visit the Truck Lagbe website. 2. Open the live chat window. 3. Send the message: “What’s the pricing for Dhaka to Chittagong?” 4. Wait for a response and measure the response time. 5. Verify if the agent replies within the 2-minute window. |  |  | FAILED
49 |  |  |  | Prevent UI language toggling mid-conversation. | UI language remains consistent (based on user’s initial choice). | ❌ Chat UI randomly switches to Bengali for subsequent messages. |  | User consistently sends messages in English. |  |  | FAILED
50 |  |  | FAQ | Verify FAQ section is accessible from all key pages. | FAQ link visible in footer on all devices. | ✅ FAQ link visible in footer on all devices. |  | 1. Navigate to homepage. 2. Check footer. 3. Switch to mobile view (320px). |  |  | PASSED
51 |  |  |  | Verify that the FAQ page loads successfully. | Page loads completely without errors. | ❌ FAQ page displays system codes/placeholders instead of human-readable text: "other.frequently-asked-question.shipper.general-questions.title" |  | Navigate to the FAQ section from the homepage/menu. |  |  | FAILED
52 |  |  |  | Check that FAQ questions can be expanded to view answers. | Corresponding answer expands below the question. | ✅ Question expanded with correct answer shown. |  | Click on any FAQ question. |  |  | PASSED
53 |  |  |  | Test question toggle behavior. | Smooth expand/collapse animation. Withstands rapid clicks. | ✅ Withstands rapid clicks. |  | Click question "How to book a truck?". Click again to collapse. Rapidly click 5+ times. |  |  | PASSED
54 |  |  |  | Verify mobile layout integrity. | No horizontal scrolling. Readable text. | ✅ Displayed as expected. |  | Resize to 320px width. Check text rendering. |  |  | PASSED
55 |  |  |  | Ensure the section for unanswered questions is visible. | Section with “Submit your question” appears. | ❌ Section not available. |  | Scroll to bottom of FAQ. |  |  | FAILED
56 |  |  | Support Ticket | Verify that the support contact form page loads successfully without errors. | Contact form should load without errors. | ✅ Loaded correctly. |  | Navigate to the "Contact Us" section. |  |  | PASSED
57 |  |  |  | Verify that users can submit the contact form with valid information. | Confirmation message shown, ticket is created. | ✅ Form submitted. |  | Fill in all required fields (Name, Email, Message), then submit. |  |  | PASSED
58 |  |  |  | Verify that the contact form displays an error when an invalid email format is entered. | Error message for invalid email format. | ❌ Invalid email format accepted. |  | Enter "samira.siddiqua@email.com" and submit. |  |  | FAILED
59 |  |  |  | Verify that the contact form prevents submission and shows validation errors when required fields are left blank. | Error highlights empty field. | ✅ Works as expected. |  | Leave "Message" field empty. Click "Submit". |  |  | PASSED
60 |  |  |  | Verify that the support contact form layout adjusts properly and remains usable on narrow or mobile screens. | No horizontal scrolling. Fields stack vertically. | ✅ Form adapts. |  | Open support page on a mobile device. Scroll through form. |  |  | PASSED
61 | Global Components |  | Header | Verify logo visibility. | Logo is displayed with the correct image. | ✅ Logo appears as expected. |  | Load the page. |  |  | PASSED
62 |  |  |  | Check that clicking the logo redirects to the homepage. | User is redirected to the homepage. | ✅ Redirects correctly. |  | Click the logo after going to another page. |  |  | PASSED
63 |  |  |  | Test logo resizing and visibility on different screen sizes (mobile, tablet, desktop). | Logo scales down without distortion or overlap. | ✅ Displays correctly on mobile. |  | Resize viewport to mobile (320px). |  |  | PASSED
64 |  |  |  | Confirm all menu items are displayed correctly. | All items are visible and legible. | ✅ All items appear as expected. |  | Check menu bar. |  |  | PASSED
65 |  |  |  | Verify each menu item links to the correct page. | Each link directs to the correct page. | ✅ Links work as expected. |  | Click each menu item. |  |  | PASSED
66 |  |  |  | Test click interactions for dropdown menus. | Dropdown expands; sub-items are clickable. | ✅ Dropdown functions as expected. |  | 1. Click dropdown. 2. Check sub-items. |  |  | PASSED
67 |  |  |  | Verify clicking the icon opens the notifications dropdown. | Dropdown shows unread notifications. | ✅ List appears. |  | Click the bell icon. |  |  | PASSED
68 |  |  | Footer | Verify contact information is displayed in footer. | Company email and phone number should be clearly visible. | ✅ All contact information displayed correctly. |  | 1. Scroll to footer section. 2. Locate contact information block. |  |  | PASSED
69 |  |  |  | Verify email link functionality in footer contact section. | Should open default email client with "To:" field pre-filled with company email. | ❌ No link attached (plain text only). |  | 1. Find email address in footer contact info. 2. Click the email link. |  |  | FAILED
70 |  |  |  | Verify phone number formatting in footer. | Should display in standard format (e.g., +1 (555) 123-4567). | ✅ Phone number formatted correctly. |  | 1. Check phone number in contact section. 2. Verify formatting. |  |  | PASSED
71 |  |  |  | Verify social media icons display in footer. | All company social media icons should be visible. | ✅ Icons display correctly. |  | 1. Scroll to footer. 2. Look for social media icons. |  |  | PASSED
72 |  |  |  | Verify social media links open correct pages. | Each icon should open correct social media page in new tab. | ✅ Links open correct pages. |  | 1. Click each social icon. 2. Check opened page. |  |  | PASSED
73 |  |  | UI/UX Elements | Verify primary CTA button visibility. | Buttons like "Hire Your Truck" stand out (color/size). | ✅ CTAs are prominent. |  | Check key pages (e.g., homepage). |  |  | PASSED
74 |  |  |  | Verify CTA button functionality. | Triggers correct action. | ✅ Actions execute properly. |  | Click primary CTAs. |  |  | PASSED
75 |  |  |  | Verify CTA with 100+ character text. | "Location not found" appears. | ✅ Actions execute properly. |  | Force long text (e.g., "ThisIsAnExtremelyLongButtonText..."). |  |  | PASSED
76 |  |  |  | Verify grid responsiveness. | CTA card reflows without overlap. | ✅ Layout adapts correctly. |  | Switch between desktop/tablet/mobile. |  |  | PASSED
77 | Blog |  | Content Organization | Verify blog categories are displayed with proper formatting and styling. | Categories like "Truck Maintenance," "Industry News" appear. | ❌ Blog categories are displayed as an unformatted list with inconsistent capitalization and redundant entries (e.g., "Truck lagbe app," "truck lagbe," "Truck rental in Bangladesh"). |  | 1. Navigate to Blog page. 2. Check sidebar/filter section. |  |  | FAILED
78 |  |  |  | Verify recent posts section exists. | "Recent Posts" section is visible. | ✅ Section appears as expected. |  | Go to Blog homepage and check the section for recent posts. |  |  | PASSED
79 |  |  |  | Verify that recent posts are sorted by date (newest first). | Posts ordered from newest to oldest. | ✅ Correct sorting. |  | Check publish dates in "Recent Posts". |  |  | PASSED
80 |  |  |  | Verify manual carousel navigation. | Advances to correct post. | ✅ Manual navigation works. |  | Click next/prev arrows. |  |  | PASSED
81 |  |  | User Engagement | Verify the blog search functionality returns relevant results for trucking-related keywords. | Displays all blog posts containing "how to hire truck" in title/content. | ❌ Displays broken/incomplete phrases (e.g., "to a using 'Lagbe' app"). Ignores quotes; returns partial matches. |  | 1. Enter "how to hire truck" in the search bar. 2. Submit. |  |  | FAILED
82 |  |  |  | Test the search feature's handling of special characters in queries. | Shows posts about truck safety (ignores special chars). | ✅ Returns valid results. |  | 1. Type "truck #safety". 2. Search. |  |  | PASSED
83 |  |  |  | Verify empty search shows all posts or helpful message. | Displays all posts or "Enter a search term" prompt. | ❌ Empty search query returns no results (blank or "Results for ''") instead of displaying all posts. |  | 1. Leave search blank. 2. Submit. |  |  | FAILED
84 |  |  |  | Verify logged-in users can submit comments on blog posts. | Comment appears instantly with username/timestamp. | ❌ Comment submission shows "comment is received" message but the comment does not appear on the blog post. |  | 1. Log in. 2. Type comment. 3. Submit. |  |  | FAILED
85 |  |  |  | Verify 500+ character comments are truncated or rejected. | Shows "Max 500 characters" error. | ❌ The system displayed a "comment received" notification but did not show the 500+ character comment on the post (no truncation or visible rejection). |  | 1. Paste long text. 2. Submit. |  |  | FAILED
86 |  |  |  | Verify social sharing buttons (Facebook/Twitter) generate correct post URLs. | Opens share dialog with blog post URL/title. | ✅ Shares proper link. |  | 1. Click share icons. 2. Check new tab. |  |  | PASSED
87 | Security |  | OWASP Standards | Verify the system sanitizes user inputs to prevent reflected XSS attacks. | Input is encoded/blocked (no script execution). | [5 empty] | Not Executed | Test not executed due to security testing restrictions. Authorization from website owner is required prior to conducting vulnerability assessments.
88 |  |  |  | Test stored XSS vulnerability in comment sections. | Comment displays as text (no image/alert). | [5 empty] | Not Executed
89 |  |  |  | Verify HTTP headers include X-XSS-Protection. | Header X-XSS-Protection: 1; mode=block is present. | [5 empty] | Not Executed
90 |  |  |  | Test login form for SQLi vulnerability. | Rejects input or shows error. | [5 empty] | Not Executed
91 |  |  |  | Verify parameterized queries in search functionality. | Returns no results or error message. | [5 empty] | Not Executed
92 |  |  |  | Test time-based SQLi in vulnerable endpoints. | Request completes in <1s (no delay). | [5 empty] | Not Executed
93 |  |  | Multi-Factor Authentication | Verify MFA enforcement for admin accounts. | Redirects to MFA setup page. | [5 empty] | Not Executed
94 |  |  |  | Test MFA bypass via session hijacking. | Requires fresh MFA code. | [5 empty] | Not Executed
95 |  |  |  | Verify MFA code expiration (5-minute TTL). | Rejects expired code. | [5 empty] | Not Executed
96 |  |  | Backups | Verify automated daily database backups. | Backup exists for last 24 hours. | [5 empty] | Not Executed
97 |  |  |  | Test backup restoration process. | All data is recovered. | [5 empty] | Not Executed
98 | Accessibility |  | Keyboard Navigation | Verify all interactive elements (buttons, links) are reachable via Tab key. | Focus moves sequentially through all clickable elements. | ✅ All elements accessible. |  | Press Tab repeatedly. |  |  | PASSED
99 |  |  |  | Test dropdown menus with keyboard (e.g., main navigation). | Dropdown opens; arrow keys navigate sub-items. | ❌ Dropdown does not open. |  | 1. Tab to menu. 2. Press Enter/Space to expand. |  |  | FAILED
100 |  |  |  | Verify focus trap in modals. | Focus cycles only within modal (can't escape to background). | ❌ Focus leaks to background. |  | 1. Open a modal (e.g., login). 2. Press Tab repeatedly. |  |  | FAILED
101 |  |  | Screen Reader Support | Verify all images have descriptive alt text. | Non-decorative images read alt text (e.g., "Red truck illustration"). | ✅ alt text announced. |  | 1. Run screen reader (e.g., NVDA). 2. Check image announcements. |  |  | PASSED
102 |  |  |  | Test ARIA labels for interactive elements (e.g., buttons). | Announces purpose (e.g., "Search button"). | ✅ ARIA labels work. |  | Navigate to a button with screen reader. |  |  | PASSED
103 |  |  | High Contrast Mode | Verify text/background contrast meets WCAG 4.5:1 ratio. | Text remains legible (e.g., black on white). | ✅ Contrast maintained. |  | 1. Enable OS high contrast mode. 2. Check text visibility. |  |  | PASSED
104 |  |  |  | Test icon visibility in high contrast mode. | Icons remain distinguishable. | ✅ Icons adapt correctly. |  | 1. Toggle high contrast. 2. Check UI icons (e.g., menu, search). |  |  | PASSED
105 |  |  | Multi-Language Support | Verify language switcher functionality. | UI/text translates to selected language. | ✅ Translation applied. |  | 1. Select "বাংলা" (Bengali). 2. Check page content. |  |  | PASSED
106 |  |  |  | Verify form validation messages in translated languages. | Shows Bengali error text (e.g., "ইমেল প্রয়োজন"). | ✅ Localized errors appear. |  | 1. Submit empty form in Bengali. 2. Check error message. |  |  | PASSED

## Test Summary Report
Testing Environment: Google Chrome Browser
Test Case Report | [5 empty] | Status | Number of Test Cases
Project Name | Bug Lagbe |  |  |  |  | Passed | 76
Module Name | User Management, Truck Booking Panel, Customer Support, Global Components, Blog, Security, Accessibilty |  |  |  |  | Failed | 19
Test Case Version | 1 |  |  |  |  | Not Executed | 11
Written By | Samira Siddiqua |  |  |  |  | Out of Scope | 0
Executed By | Samira Siddiqua |  |  |  |  | Total | 106
Reviewed By | Ehsanul Alam Sabbir
Test Execution Report
Test Cases | Passed | Failed | Not Executed | Out Of Scope | Total
Test Cases | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 76 | 19 | 11 | 0 | 106
Grand Total | 76 | 19 | 11 | 0 | 106
Limitations
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Reports
Bug Reporting
#SL 01
Issue: Email Verification – Confirmation link leads to "Cannot GET" error (404)
Reproducing Steps:
1. Go to edit profile and add email. 2. Save a new email address. 3. Open the confirmation email received. 4. Click the verification link.
Environment: OS: Windows 11 ¦ Browser: Chrome 125 ¦ Device: ASUS Vivobook (Model: X1504VA_X1504VA)
Module: User Management
Priority: P0
Severity: High
Screenshot: EmailVerification_Error.jpg
Expected result: A confirmation email with correct formatting and a working verification link is sent to the updated email, and clicking the link successfully verifies the email on the Truck Lagbe website.
Actual result: Verification link leads to: Cannot GET /appApi/117/confirm/userEmailVerification.
Bug Reporting
#SL 02
Issue: "Resend Verification Email" button fails to deliver new verification email.
Reproducing Steps:
1. Click "Resend Verification Email".​ 2. Open the new email and click the link. 3. Check the profile.
Environment: OS: Windows 11 ¦ Browser: Chrome 125 ¦ Device: ASUS Vivobook (Model: X1504VA_X1504VA)
Module: User Management
Priority: P1
Severity: High
Screenshot: N/A
Expected result: 1. System sends a new email within 1-2 minutes. 2. Link works; email is verified successfully. 3. Email status updates to "Verified".
Actual result: No email received after clicking "Resend".
Bug Reporting
#SL 03
Issue: Cached authenticated content remains temporarily accessible after logout via browser back navigation.
Reproducing Steps:
1. Log in to the Truck Lagbe website. 2. Log out from the website using the Logout button. 3. After being redirected to the login page, click on the browser back button.
Environment: OS: Windows 11 ¦ Browser: Chrome 125 ¦ Device: ASUS Vivobook (Model: X1504VA_X1504VA)
Module: User Management
Priority: P1
Severity: High
Screenshot: SessionPersistence_AfterLogout_BackButton.jpg
Expected result: The user should not be able to access any of the previous pages that require an active session. The website should redirect the user back to the login page if they try to access any secure page using the back button.
Actual result: After pressing the back button: The dashboard page loads for several minutes (extended delay). Eventually, it confirms the logged-out state. Reproducible in both Chrome and Edge.
Bug Reporting
#SL 04
Issue: Profile name field accepts invalid characters (numbers, symbols) without validation.
Reproducing Steps:
1. Navigate to the Profile Settings page. 2. Enter an invalid name containing special characters or numbers (e.g., "J0hn D0e!@#"). 3. Click on the Save/Update button.
Environment: OS: Windows 11 ¦ Browser: Chrome 125 ¦ Device: ASUS Vivobook (Model: X1504VA_X1504VA)
Module: User Management
Priority: P1
Severity: Medium-High
Screenshot: ProfileName_InvalidInputAccepted.jpg
Expected result: The system should display an error message indicating invalid input. The name should not be updated.
Actual result: System accepts all invalid names (numbers, special characters, single letters) without validation or error messages.
Bug Reporting
#SL 05
Issue: Profile photo upload appears successful but fails silently (no API call, no persistence).
Reproducing Steps:
1. Navigate to the Profile Settings page. 2. Click on the profile picture section to upload a new photo. 3. Select a valid image file (e.g., JPG, PNG, or JPEG within the allowed size limit). 4. Click the Upload/Save button. 5. Refresh the page to check if the updated profile picture is displayed correctly.
Environment: OS: Windows 11 ¦ Browser: Chrome 125 ¦ Device: ASUS Vivobook (Model: X1504VA_X1504VA)
Module: User Management
Priority: P1
Severity: High
Screenshot: ProfilePhoto_UploadFailure_Silent.jpg
Expected result: The profile photo should be successfully updated and displayed on the user's profile.
Actual result: Failure Observed: Thumbnail preview works, but clicking Update does nothing (no API call, no error). After refresh, the old/default image remains (upload failed silently).
Bug Reporting
#SL 06
Issue: Live chat widget is not responsive on small screens (cuts off content).
Reproducing Steps:
1. Open the Truck Lagbe website on a desktop, tablet, and mobile device. 2. Verify the responsiveness of the chat window.
Environment: OS: Windows 11 ¦ Browser: Chrome 125 ¦ Device: ASUS Vivobook (Model: X1504VA_X1504VA)
Module: Customer Support
Priority: P1
Severity: Medium-High
Screenshot: ChatWidget_NonResponsive_Mobile.jpg
Expected result: The chat window should adjust its layout appropriately on different screen sizes (e.g., desktop, tablet, mobile).
Actual result: Live chat widget cuts off on small screens.
Bug Reporting
#SL 07
Issue: Live Chat Agent Fails to Respond to Pricing Query Within 2-Minute Timeframe.
Reproducing Steps:
1. Visit the Truck Lagbe website. 2. Open the live chat window. 3. Send the message: “What’s the pricing for Dhaka to Chittagong?” 4. Wait for a response and measure the response time. 5. Verify if the agent replies within the 2-minute window.
Environment: OS: Windows 11 ¦ Browser: Chrome 125 ¦ Device: ASUS Vivobook (Model: X1504VA_X1504VA)
Module: Customer Support
Priority: P1
Severity: Medium-High
Screenshot: LiveChat_NoResponse_PricingQuery.jpg
Expected result: Agent responds within ≤ 2 minutes.
Actual result: The live chat agent did not respond to the pricing query within the 2-minute timeframe (no response received ultimately).
Bug Reporting
#SL 08
Issue: Live Chat UI Language Inconsistently Switches Mid-Conversation (English → Bengali)
Reproducing Steps:
1. Visit the Truck Lagbe website. 2. Open the live chat window. 3. Sends messages in English consistently.
Environment: OS: Windows 11 ¦ Browser: Chrome 125 ¦ Device: ASUS Vivobook (Model: X1504VA_X1504VA)
Module: Customer Support
Priority: P2
Severity: Medium
Screenshot: N/A
Expected result: UI language remains consistent (based on user’s initial choice).
Actual result: Chat UI randomly switches to Bengali for subsequent messages.
Bug Reporting
#SL 09
Issue: FAQ Page Displays System Codes/Placeholders Instead of Human-Readable Text.
Reproducing Steps:
Navigate to the FAQ section from the homepage/menu.
Environment: OS: Windows 11 ¦ Browser: Chrome 125 ¦ Device: ASUS Vivobook (Model: X1504VA_X1504VA)
Module: Customer Support
Priority: P2
Severity: Medium
Screenshot: FAQ_Page_PlaceholderText_Error
Expected result: Page loads completely without errors.
Actual result: FAQ page displays system codes/placeholders instead of human-readable text: "other.frequently-asked-question.shipper.general-questions.title"
Bug Reporting
#SL 10
Issue: Missing "Submit Your Question" Section in FAQ Page.
Reproducing Steps:
Scroll to bottom of FAQ.
Environment: OS: Windows 11 ¦ Browser: Chrome 125 ¦ Device: ASUS Vivobook (Model: X1504VA_X1504VA)
Module: Customer Support
Priority: P3
Severity: Medium
Screenshot: FAQ_Missing_SubmitQuestion_Section
Expected result: Section with “Submit your question” appears.
Actual result: Section not available.
Bug Reporting
#SL 11
Issue: Contact Form Accepts Invalid Email Format Without Validation Error.
Reproducing Steps:
1. Navigate to the Contact Us page. 2. Enter an invalid email format (e.g., samira.siddiqua@email.com). 3. Submit the form.
Environment: OS: Windows 11 ¦ Browser: Chrome 125 ¦ Device: ASUS Vivobook (Model: X1504VA_X1504VA)
Module: Customer Support
Priority: P3
Severity: Medium
Screenshot: ContactForm_InvalidEmail_NoValidationError
Expected result: Error message for invalid email format.
Actual result: Invalid email format accepted.
Bug Reporting
#SL 12
Issue: Footer Email Contact Link Non-Functional (Plain Text Instead of Mailto Link).
Reproducing Steps:
1. Find email address in footer contact info. 2. Click the email link.
Environment: OS: Windows 11 ¦ Browser: Chrome 125 ¦ Device: ASUS Vivobook (Model: X1504VA_X1504VA)
Module: Global Components
Priority: P3
Severity: Low-Medium
Screenshot: Footer_EmailLink_NonFunctional
Expected result: Should open default email client with "To:" field pre-filled with company email.
Actual result: No link attached (plain text only).
Bug Reporting
#SL 13
Issue: Blog Categories Displayed with Inconsistent Formatting, Capitalization, and Redundant Entries.
Reproducing Steps:
1. Navigate to Blog page. 2. Check sidebar/filter section.
Environment: OS: Windows 11 ¦ Browser: Chrome 125 ¦ Device: ASUS Vivobook (Model: X1504VA_X1504VA)
Module: Blog
Priority: P3
Severity: Low-Medium
Screenshot: Blog_Categories_InconsistentFormatting
Expected result: Categories like "Truck Maintenance," "Industry News" appear.
Actual result: Blog categories are displayed as an unformatted list with inconsistent capitalization and redundant entries (e.g., "Truck lagbe app," "truck lagbe," "Truck rental in Bangladesh").
Bug Reporting
#SL 14
Issue: Blog Search Returns Irrelevant/Broken Results for Trucking-Related Keywords.
Reproducing Steps:
1. Enter "how to hire truck" in the search bar. 2. Submit.
Environment: OS: Windows 11 ¦ Browser: Chrome 125 ¦ Device: ASUS Vivobook (Model: X1504VA_X1504VA)
Module: Blog
Priority: P2
Severity: Medium
Screenshot: BlogSearch_BrokenResults_ExactPhrase
Expected result: Displays all blog posts containing "how to hire truck" in title/content.
Actual result: Displays broken/incomplete phrases (e.g., "to a using 'Lagbe' app"). Ignores quotes; returns partial matches.
Bug Reporting
#SL 15
Issue: Empty Search Returns No Results Instead of Showing All Posts.
Reproducing Steps:
1. Leave search blank. 2. Submit.
Environment: OS: Windows 11 ¦ Browser: Chrome 125 ¦ Device: ASUS Vivobook (Model: X1504VA_X1504VA)
Module: Blog
Priority: P3
Severity: Low-Medium
Screenshot: BlogSearch_EmptyQuery_NoResults
Expected result: Displays all posts or "Enter a search term" prompt.
Actual result: Empty search query returns no results (blank or "Results for ''") instead of displaying all posts.
Bug Reporting
#SL 16
Issue: Comment Submission Fails Silently for Logged-In Users.
Reproducing Steps:
1. Log in. 2. Type comment. 3. Submit.
Environment: OS: Windows 11 ¦ Browser: Chrome 125 ¦ Device: ASUS Vivobook (Model: X1504VA_X1504VA)
Module: Blog
Priority: P1
Severity: High
Screenshot: Blog_Comment_Submission_Failure
Expected result: Comment appears instantly with username/timestamp.
Actual result: Comment submission shows "comment is received" message but the comment does not appear on the blog post.
Bug Reporting
#SL 17
Issue: 500+ Character Comments Silently Fail Without Proper Validation
Reproducing Steps:
1. Log in to any user account 2. Navigate to a blog post with comments enabled 3. Paste or type 500+ characters into the comment box 4. Click Submit
Environment: OS: Windows 11 ¦ Browser: Chrome 125 ¦ Device: ASUS Vivobook (Model: X1504VA_X1504VA)
Module: Blog
Priority: P1
Severity: High
Screenshot: N/A
Expected result: Shows "Max 500 characters" error.
Actual result: The system displayed a "comment received" notification but did not show the 500+ character comment on the post (no truncation or visible rejection).
Bug Reporting
#SL 18
Issue: Dropdown Menu Does Not Open via Keyboard Navigation (Accessibility Failure).
Reproducing Steps:
1. Tab to menu. 2. Press Enter/Space to expand.
Environment: OS: Windows 11 ¦ Browser: Chrome 125 ¦ Device: ASUS Vivobook (Model: X1504VA_X1504VA)
Module: Accessibility
Priority: P1
Severity: High
Screenshot: N/A
Expected result: Dropdown opens; arrow keys navigate sub-items.
Actual result: Dropdown does not open.
Bug Reporting
#SL 19
Issue: Modal Focus Leaks to Background Content (Keyboard Trap Failure)
Reproducing Steps:
1. Open a modal (e.g., login). 2. Press Tab repeatedly.
Environment: OS: Windows 11 ¦ Browser: Chrome 125 ¦ Device: ASUS Vivobook (Model: X1504VA_X1504VA)
Module: Accessibility
Priority: P1
Severity: High
Screenshot: N/A
Expected result: Focus cycles only within modal (can't escape to background).
Actual result: Focus leaks to background.